## DWM
Pilot : Tradesphere
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12

## Phases
Tradesphere Project Tracker
Task ID | Phase | Task Name | Dependency Task ID | Start Date | Duration (Days) | End Date | Status | weekend off included
1 | Phase 1 | Requirement Analysis & Solution Design |  | 2026-06-08 | 9 | 2026-06-17 | Completed | Yes | Completed
2 | Phase 2 | Database Design & Architecture Setup | 1 | 2026-06-18 | 18 | 2026-07-06 | In-progress | Yes | Not Started
3 | Phase 3 | Authentication Module | 2 | 2026-07-07 | 7 | 2026-07-14 | Completed | Yes | In-Progress
4 | Phase 4 | Security Module | 3 | 2026-07-15 | 2 | 2026-07-17 | In-progress | Yes
5 | Phase 5 | Employee Module | 4 | 2026-07-18 | 7 | 2026-07-25 | Completed | Yes
6 | Phase 6 | Territory Module | 5 | 2026-07-26 | 7 | 2026-08-02 | Not Started | Yes
7 | Phase 7 | Promoter Module | 6 | 2026-08-03 | 7 | 2026-08-10 | Not Started | Yes
8 | Phase 8 | Beats & Beat Assignment Module | 7 | 2026-08-11 | 10 | 2026-08-21 | Not Started | Yes
9 | Phase 9 | Retailer Module | 8 | 2026-08-22 | 7 | 2026-08-29 | Not Started | Yes
10 | Phase 10 | Attendance And EOD Module | 9 | 2026-08-30 | 9 | 2026-09-08 | Not Started | Yes
11 | Phase 11 | Visit Module | 10 | 2026-09-09 | 9 | 2026-09-18 | Not Started | Yes
12 | Phase 12 | Retailer Feedback Module | 11 | 2026-09-19 | 5 | 2026-09-24 | Not Started | Yes
13 | Phase 13 | Product Module | 12 | 2026-09-25 | 5 | 2026-09-30 | Not Started | Yes
14 | Phase 14 | Retailer Stock Management | 13 | 2026-10-01 | 9 | 2026-10-10 | Not Started | Yes
15 | Phase 15 | Order Module | 14 | 2026-10-11 | 7 | 2026-10-18 | Not Started | Yes
16 | Phase 16 | UI/UX Design(Portal + App) | 15 | 2026-10-19 | 19 | 2026-11-07 | Not Started | Yes
17 | Phase 17 | Dashboard & Reporting | 16 | 2026-11-08 | 9 | 2026-11-17 | Not Started | Yes
18 | Phase 18 | Testing, Bug fixing | 17 | 2026-11-18 | 9 | 2026-11-27 | Not Started | Yes
19 | Phase 19 | Deployment And Go-live Suppot | 18 | 2026-11-28 | 9 | 2026-12-07 | Not Started | Yes
|  | Final Date | 2026-12-07
Formulas:
End Date = [Start Date]+[Duration (Days)]
Start Date = [End Date, row above]+1

## Project Timeline
Task ID | Phase | Task Name | Dependency (Task ID) | Start Date | Duration (Days) | End Date | Status
1 | Planning | Project Kickoff |  | 08-06-2026 | 2 |  | Not Started
2 | Planning | Requirement Gathering | 1 |  | 5
3 | Design | Solution Design | 2 |  | 4
4 | Implementation | Development Phase 1 | 3 |  | 6
5 | Implementation | Development Phase 2 | 4 |  | 5
6 | Testing | System Testing | 5 |  | 4
7 | UAT | User Acceptance Testing | 6 |  | 3
8 | Go-Live | Production Deployment | 7 |  | 2